## RunSimul
pRisk
Parameter | Value
Number of simulations | 3000
Cell to analyse | #VALUE!
Plot | pdf
Result: Mean | 2.0085
Result: SD | 0.38099
Result: Min | 1.0578
Result: Max | 2.9075
Note on A4: Specify number of simulation to run
Note on A5: Enter a reference to the cell that contains the "result".
Note on A6: Enter plot type: PDF = Probability density function CDF = Cumulative distribution function NONE = Do not update plot
Run

## MCS
Activity | L | M | H | Start | Duration | End | Formulas, Start
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!

## SSP
Activity | L | M | H | mi | si2 | EiF | ViF | Formula ViF
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
|  |  |  | 0 | 0 |  |  | #VALUE!
[6 empty] | E(Final)= | 0
[6 empty] | SD(Final)= | 0
Specification for Succesive Schedue Planning

## PERT
Activity | L | M | H | mi | si2 | In crit. Path | E | V
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
[6 empty] | Sum | 0 | 0 | 0

## PDFPlot (hidden)
x | Probability density function
0.72048 | 0
0.72048 | 0
0.7417 | 0
0.76291 | 0
0.78413 | 0
0.80534 | 0
0.82656 | 0
0.84778 | 0
0.86899 | 0
0.89021 | 0
0.91142 | 0
0.93264 | 0
0.95386 | 0
0.97507 | 0
0.99629 | 0
1.0175 | 0
1.0387 | 0
1.0599 | 0.00033333
1.0812 | 0.0016667
1.1024 | 0.001
1.1236 | 0.0013333
1.1448 | 0.0023333
1.166 | 0.003
1.1872 | 0.0026667
1.2084 | 0.001
1.2297 | 0.003
1.2509 | 0.006
1.2721 | 0.0016667
1.2933 | 0.004
1.3145 | 0.0073333
1.3357 | 0.007
1.357 | 0.0043333
1.3782 | 0.006
1.3994 | 0.0076667
1.4206 | 0.01
1.4418 | 0.0073333
1.463 | 0.010667
1.4843 | 0.011
1.5055 | 0.011667
1.5267 | 0.007
1.5479 | 0.012333
1.5691 | 0.012667
1.5903 | 0.012667
1.6116 | 0.013333
1.6328 | 0.013667
1.654 | 0.011
1.6752 | 0.017667
1.6964 | 0.018
1.7176 | 0.020333
1.7388 | 0.020667
1.7601 | 0.023667
1.7813 | 0.018
1.8025 | 0.017
1.8237 | 0.014333
1.8449 | 0.017667
1.8661 | 0.018333
1.8874 | 0.018
1.9086 | 0.017
1.9298 | 0.019333
1.951 | 0.021333
1.9722 | 0.023333
1.9934 | 0.015
2.0147 | 0.019667
2.0359 | 0.019333
2.0571 | 0.019
2.0783 | 0.022
2.0995 | 0.017
2.1207 | 0.017667
2.142 | 0.019
2.1632 | 0.019667
2.1844 | 0.019667
2.2056 | 0.018667
2.2268 | 0.018
2.248 | 0.018667
2.2692 | 0.020667
2.2905 | 0.018333
2.3117 | 0.014333
2.3329 | 0.018333
2.3541 | 0.014333
2.3753 | 0.018667
2.3965 | 0.016
2.4178 | 0.011333
2.439 | 0.009
2.4602 | 0.014333
2.4814 | 0.009
2.5026 | 0.011
2.5238 | 0.011333
2.5451 | 0.0083333
2.5663 | 0.009
2.5875 | 0.0096667
2.6087 | 0.0076667
2.6299 | 0.007
2.6511 | 0.0073333
2.6724 | 0.0063333
2.6936 | 0.005
2.7148 | 0.0056667
2.736 | 0.0053333
2.7572 | 0.0043333
2.7784 | 0.0066667
2.7996 | 0.0036667
2.8209 | 0.002
2.8421 | 0.00066667
3.2664 | 0.00066667

## MRL
MTTF | 80
lambda | 0.01133 | #VALUE!
alpha | 4 | Aging parameter
t | 40
MRL | #VALUE! | #VALUE!
Age of death | #VALUE!