## Sheet1
Question 1: What is the planned execution time for the interior construction using a 1-week takt?
Formula to be used:
Execution time = (Number of wagons + number of sections -1)*Takt time
Execution time = | (12+7-1)*5 | 90
Question 2: If the takt time is changed to 1 day, what will the execution time for the interior construction be?
If the number of craftspeople is to remain the same, the size of the sections must be reduced in correspondance to the takt time.
Then each section will be 1/5 of a floor, or two apartments, with 5 sections per floor
That means a total of 5*7 sections, = 35
Formula to be used:
Execution time = (Number of wagons + number of sections -1)*Takt time
Execution time = | (12+35-1)*1 | 46
Question 3: Calculate the following variables when using a takt time of 1 day and when the whole train is inside the building:
Batch size = the size of the sections = |  | 2 apartments
Cycle time per apartment = the time it takes the whole train to move through the apartment
With 12 wagons and a takt time of 1 day, it will take 12 days
Work in progress = the sum of apartments which any wagon of the train is "visiting"
With 12 wagons and 2 apartments per section, thw work is progress = 24 apartments